## WBS
Sl.Num | Task | Subtask | Responsibility | Time(Hrs) | Remarks
1 | Creating the basic templates | Designing the Nav bar | Team | 7 | nil
|  | Designing the Footer | Mouli | 4 | nil
|  | Finalizing the color combination | Team | 1 | nil
|  | Editing the logo | Bertin | 1 | nil
|  | Choosing the font | Team | 1 | nil
2 | Developing the Home page | Adding the banner | Divya &Nagashree | 4 | nil
3 | Developing the About us page | Adding the chairman 's message |  | 1 | nil
|  | Adding Vision, Mission,values |  |  | nil
|  | Merging the team code of v4 template |  | 5 | nil
|  | Adding the additional Info to above mentioned |  | 4 | nil
|  | Adding the code of statical data from template V1 |  | 5 | nil
|  | Editing the resolution and size of the images related to Task 3 |  | 6 | nil
5 | Development of Clinical Service | Merging the our services code of template V2 | Aparna | 5 | nil
|  | Creation of clinical service page |  | 3.5 | nil
|  | Editing and resizing of images |  | 5 | nil
|  | Adding the content and images |  | 3 | Dependancy on BN for Content
| Supportive Services | Creating a page for Supportive Services | Ankitha | 5 | nil
|  | Preparing the HD logos for TPA and CorporateEmpanelments | Shreesha | 5 | nil
6 | Community Services | Creation of page for Community Services | Bertin and Rekha | 4 | nil
7 |  | Selecting and editing of images |  | 5 | nil
|  | Adding the content and images |  | 3 | nil
| Gallery page | Developing the Gallery page | Shreesha | 7 | nil
|  | Selecting and editing of images | Bertin | 6 | nil
| Blog | Linking from BN website to Blog | Bertin | 1 | nil
8 | Testimonials | Creation of testimonial page | Divya | 5 | nil
9 |  | Adding content for testimonial | Divya | 2 | nil
| Branches | Creation of page for Branches | Nagashree and Mouli | 6 | nil
|  | Editing the existing image |  | 3 | nil
| Fix Up appointment | Creation of appointment form | Rekha | 4 | nil
|  | Selecting and editing of images | Rekha | 1 | nil
10 | Developing Contact Us page | Creating the contact us form | Divya | 3 | nil
|  | Selecting and editing of images | Divya | 2 | nil
11 | Career page | Creation of career page | Shreesha and Ankitha | 4 | No Info has been given about Career page
12 | Merging the code on daily basis | nil | Nagashree and Aparna | 10 | 2hrs per day
13 | Discussing each page's layout with team on daily basis | nil | Team | 10 | 2hrs per day
14 | Modifications after each review | nil | respective person | 10 | 2hrs per day
Total |  | 151.5
Buffer Time |  | 50
Grand Total |  | 201.5 Hrs